###### Business Development Project Steps

Business Development Projects are typically fast track projects

Date Complete/Received

Prior to and/or during Application Preparation

Request Application for Business Development Assistance

(Form can be found on SCDOC website)

  - Include company information (i.e.-name, type, capital investment,

number of new jobs to be created, etc.)

  - Include Project Map

  - Include Cost Estimate or Preliminary Engineering Report

Start Environmental Review Process

(Requirements differ depending on type of assistance)

Determine classification for activity, assessment and level of 
clearance needed

Publish/post findings/intent to request release of funds 
	(if applicable)

Submit request for release of funds

Hold Public Hearing(s)

Needs Assessment, if not current (must have ED component)

Application Public Hearing

GA/Administrator/Employment Security Commission (if necessary)
to conduct site visit and meet with company officials

- Discuss their commitment (# jobs, %LMI) and record-keeping

requirements; required application information and Performance

Agreement

- Discuss timeframe

- Advise that local administrator will conduct an on-site visit
quarterly and that Grants Administration will monitor when
initial hiring is complete

Procure engineer and submit contract for approval (n/a if being paid for by

locality)

Execute contract

Begin Acquisition following URA  (if applicable)

###### Business Development Project Steps (continued)

Date Complete/Received

Application Preparation (45 days maximum to complete)

CDBG Purpose/Outcome for Economic Development Projects

  - Economic Opportunities

  - Access to or availability of new job creation or retention

Information Needed from County

  - Cash Match or other equivalent information (ex:  FILOT);

prior approval req’d by GA

  - PER-Who to pay for Engineer?

Information Needed by Company

  - Commitment Letter

  - Company Information Sheet

  - Hiring Plan

  - Financial Information (if grant is for Direct Assistance)

  - Advise company not to begin construction activities until

Environmental is cleared

Post Grant Award

Clear any special conditions placed on the grant

Submit Performance Agreement for review and approval

prior to release funds

Begin satisfying Start Up Checklist items

Clear and submit ERR

Submit Section 504 Schedule

Submit Fair Housing Plan

Submit Executed Performance Agreement

Submit financial forms to Finance

Subrecipient Agreement, if applicable

Prepare subrecipient agreement

Submit subrecipient agreement to Grants Administration
for approval

Execute subrecipient agreement, after Grants	
Administration approval

###### Business Development Project Steps (continued)

Date Complete/Received

Procure construction contractor and submit proposed contract to

GA for approval

Verify wage decision, execute contract and issue notice to
proceed

Hold pre-construction conference

Construct Project

Review contractor payments/change orders

Labor Standards (also req’d for Direct Assistance projects involving

equipment installation)

Review contractor payroll

Conduct employee interviews

Track/Monitor Job Creation

Grants Administration Monitoring

Programmatic

Include all programmatic information

Jobs

Arrange for meeting with the company

Finalize all payments

Deobligate grant (if job creation not complete, close pending beneficiaries)

Complete close-out requirements

Advertise for and conduct a final performance hearing
(include # of jobs created)

Obtain as-built drawings from engineer (if applicable)

Include digital photographs (if applicable)