## Sheet1
- SAMPLE -
Check one: | Initial | X |  |  |  | P-1 IMPLEMENTATION SCHEDULE FOR CDBG GRANTEES
| Revised | [6 empty] | GRANTS ADMINISTRATION
Grantee: |  | Town of Blue River | [6 empty] | Grant #: |  | 4-L-02-060 | [7 empty] | Date: | September 2, 2002
Approved Grant Period: |  | 8/02-8/04 | [6 empty] | Prepared by: |  | Bill Williams
1. Implementation Steps: List (in sequence) all major steps necessary to complete the project activity (for example, procurement of engineer, acquisition, bids, construction, final inspection, and close-out).
2. Schedule: Using "X's", show the proposed schedule for completion of each implementation step. For steps that are complete, use the actual line for the X's. For steps that have yet to occur, use the target line
for your X's.
Note: This project grid allows for projected implementation scheduling over a period of 24 months. Indicate the beginning and ending month and year of project implementation.
Implementation | Month/
Steps | Year | 8/02 | 9/02 | 10/02 | 11/02 | 12/02 | 1/03 | 2/03 | 3/03 | 4/03 | 5/03 | 6/03 | 7/03 | 8/03 | 9/03 | 10/03 | 11/03 | 12/03 | 1/04 | 2/04 | 3/04 | 4/04 | 5/04 | 6/04 | 7/04 | 8/04
Grant Award | Target | X
Actual
Environmental Review | Target | X | X | X
Actual
Start-Up Checklist Requirements | Target | X | X | X
Actual
Engineering - Procurement | Target |  | X | X
Actual
Engineering - Project Design | Target |  |  |  | X | X | X
Actual
DHEC Approval - Project Design | Target | [5 empty] | X | X
Actual
Acquisition of Easements | Target | [6 empty] | X | X | X
Actual
Construction - Bidding | Target | [9 empty] | X | X
Actual
Construction - Award Contract | Target | [11 empty] | X
Actual
Pre-Construction Conference | Target | [11 empty] | X
Actual
Construction - Main Lines | Target | [12 empty] | X | X | X | X | X | X | X | X
Actual
DCGP Monitoring | Target | [17 empty] | X
Actual
DHEC Inspection - Main Lines | Target | [20 empty] | X
Actual
Unit Connections | Target | [21 empty] | X | X
Actual
Grant Closeout | Target | [23 empty] | X | X
Actual